## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Initial setup and first user story | 1 | 2024-01-06 | Repository setup and implementation of the navbar.
Front-end for second user story | 1.5 | 2024-01-06 | Front-end for the Houses component, API not yet implemented.
API implementation for second user story | 0.5 | 2024-01-07 | Dummy data replaced with actual API information
Search bar implementation (3rd user story) | 1 | 2024-01-07 | Search bar functionality added, user can now use it to filter houses.
Sort implementation (4th user story) | 1 | 2024-01-07 | Buttons for sorting with price and size added
House details (5th user story) | 2 | 2024-01-10 | User can click on a house in Houses.vue and see details of said house
Creation of new houses (6th user story) | 5 | 2024-01-12 | New houses can now be created by the user
Deleting and editing (7th, 8th and 9th user st | 5 | 2024-01-13 | User can delete and edit the listings they have made
Mobile version | 3 | 2024-01-13 | User can now see the mobile version when their screen is small enough
Responsiveness | 3 | 2024-01-14 | Responsiveness added to all pages
About us | 0.5 | 2024-01-14 | About us page | x
Removing hash in URL | 0.2 | 2024-01-28 | Updated router history mode to createWebHistory() (no hash)
Refactored JS files | 0.2 | 2024-01-28 | Refactored JS files to fix inconsistent indentation
Search bar feedback implementation | 0.4 | 2024-01-28 | Implemented feedback for the search bar
Validation fix for the construction year | 0.2 | 2024-01-28 | User sees a validation error for the construction year now (if its below 1901)
API service refactor according to DRY | 1 | 2024-01-28 | Implemented feedback regarding the API service
Fixed console errors | 0.5 | 2024-01-28 | No more console errors when creating/editing/deleting houses.
"/houses/" stays in URL | 0.5 | 2024-01-29 | Houses navigation item stays active in URL
Price formatting | 0.2 | 2024-01-29 | Added price formatting for easier readability of prices
No result image and text | 0.5 | 2024-01-29 | If there are no search results the relevant image and text is shown
Getter added in houses store | 0.2 | 2024-01-29 | Getter added in houses store and used in houses.vue
Number only fields added | 0.2 | 2024-01-29 | Number only fields added in NewListing.vue and EditListing.vue
House detail store added | 1.5 | 2024-01-29 | No more need to set each variable manually in the HouseDetails.vue
Total amount of hours | 29.1